## 24-Month Calendar
Premier Utah Real Estate — 24-Month Marketing Calendar
Path B baseline · Launch: Q1 2027 · Phase 2 SLC gate: Month 15 · Total budget: $450K
Month | Date | Phase | Theme | Major Initiative | SEO / Content | Paid Channels | Brand / PR | Builder & PM | Internal / Ops | Budget ($) | Primary KPI Target
1 | Jun 2026 | Phase 0 — Build | Discovery & strategy | Brand positioning lock; competitive audit; sitemap + wireframes approved | Keyword research deep-dive: Tooele County clusters, lifestyle terms, competitor gap analysis | Paid paused — no spend yet. Account audits + pixel placement on existing site. | Voice & tone guidelines circulated to team. Begin photography RFP. | UpDwell stakeholder kickoff. PM division process docs reviewed. | Marketing team onboarded to brand. CRM (Follow Up Boss) implemented. | 8000 | Strategy doc + sitemap signed off
2 | Jul 2026 | Phase 0 — Build | Design system & content audit | High-fidelity homepage + listing detail design comps; design system 1.0 | Audit existing 200+ pages on legacy site. Map 301 redirects. | Pre-launch retargeting list build on existing site (warming audience for re-engagement at launch). | Hire local Tooele photographer; brand photoshoot scheduled. | UpDwell Highland community plan finalized. Floor plan assets gathered. | Tooele agent training: lifecycle positioning, voice, social standards. | 12000 | Design comps + photography contract
3 | Aug 2026 | Phase 0 — Build | Development sprint 1 | Homepage + listing detail built. MLS feed integration begins. | First 12 neighborhood-page outlines written. Blog editorial calendar drafted. | Continue audience-building. Reserve Google Ads brand-defense budget for launch. | Photography production: agents (15), listings (30), neighborhoods (12). | PM owner-statement template redesigned. Tenant portal wireframes. | Internal social-media playbook drafted. Agent video coaching begins. | 18000 | Homepage shippable in staging
4 | Sep 2026 | Phase 0 — Build | Development sprint 2 | Neighborhood pages, agent bios, market reports template, CMS spinning | Write first 6 neighborhood pages (Tooele, Stansbury, Grantsville, Erda, Lake Point, Stockton). | Plan paid launch creative. Test Meta Lead Form variant for buyer leads on existing site. | Video kit: agent intros (15), neighborhood reels (6), hero brand reel. | Highland Community microsite content drafted. Lot/floor plan visuals approved. | CRM-to-site form integrations live. Marketing automation flows mapped. | 16000 | Neighborhood pages content-complete
5 | Oct 2026 | Phase 0 — Build | Lifecycle Account + IDX | Lifecycle Account auth + dashboard + collections + saved searches; conversational search | Write seller and first-time-buyer evergreen guides. Begin market-report October data. | Begin Meta retargeting at low spend ($1.5K) to warm audiences for launch. | Press release draft: "Premier Launches Lifecycle Real Estate Platform." | Highland Community grand opening planning begins. | Customer service scripts updated for Lifecycle Account questions. | 14000 | Lifecycle Account in staging
6 | Nov 2026 | Phase 0 — Build | QA + accessibility + soft launch prep | Performance pass, accessibility audit, content QA, 301 redirect testing, beta to internal team | October Tooele Market Report published on staging. Holiday SEO content live. | Launch creative briefs finalized: Google, Meta, YouTube, Nextdoor. | Soft-launch press relationships: Tooele Transcript Bulletin, KSL.com, Building Salt Lake. | Builder partnership announcement coordinated for launch. | Agent dry-run of full Lifecycle Account experience. | 12000 | All systems green; readiness sign-off
7 | Dec 2026 | Phase 1 — Tooele Foundation | Soft launch + holiday lead capture | 20% traffic soft launch (4th week of Dec). 301 mapping live. Monitoring dashboards on. | Publish 4 evergreen guides; first official market report on new site. | Begin Google brand-defense ($2.5K). Light Meta retargeting ($2K). | "What we built" team email + social announcement. Soft press. | Highland sales-center holiday hours promoted. | Team holiday party doubles as launch celebration. | 14000 | Site uptime 99.9%, zero P0 bugs
8 | Jan 2027 | Phase 1 — Tooele Foundation | Full launch + spring market prep | 100% traffic. Full launch press: "Premier debuts lifecycle platform." Local media tour. | Publish January market report; first 6 lifestyle-cluster pages; agent bios all live. | Full paid spend live: Google ($4K), Meta ($3K), YouTube pre-roll ($2K), Nextdoor ($1K). | Coordinated PR push: Tooele Transcript feature, KSL business segment pitch, Building SLC piece. | UpDwell Q1 inventory + builder incentive promoted heavily. | First monthly executive dashboard delivered. KPI baselines locked. | 22000 | 350 leads · CPL <$60 · 95+ organic keywords ranking
9 | Feb 2027 | Phase 1 — Tooele Foundation | Spring market kickoff | First Premier-hosted webinar: "Tooele 2027 Market Outlook." | Publish 8 blog posts. Spring buyer guide. Sellers checklist refreshed. | Lift Google + Meta to $9K combined. First Meta video creative test. | Webinar promotion. Pitch local podcast guest spots for Tammy + Steve. | Highland model home open every Saturday. Builder Reels start. | Internal monthly review meeting standardized. | 20000 | 450 leads · 8 transactions attributable to digital
10 | Mar 2027 | Phase 1 — Tooele Foundation | Spring buying season | Major Spring Open House Weekend (8 listings simultaneously). PR coordinated. | 10 new posts including "Tooele neighborhoods compared" pillar piece. | Boost paid to $12K. Test YouTube long-form on agent channel. | Open House Weekend earned-media push. Drone-shot reel for each property. | Highland Phase 2 lots released. Promoted across paid + organic. | Photographer retainer renewed for monthly shoots. | 22000 | 550 leads · CPL <$50 · 10 sold-side wins
11 | Apr 2027 | Phase 1 — Tooele Foundation | Builder push + investor audience activation | Launch dedicated Investor landing page + email sequence (PM + brokerage cross-sell). | Investor-focused content: 1031 exchange guide, Tooele cash-on-cash analysis, BRRRR primer. | Add LinkedIn paid + Google investor keywords. Test investor lookalike on Meta. | Press: investor positioning piece. Local BiggerPockets meetup sponsorship. | PM department new-owner welcome sequence revamped. | Hire content lead (in-house). Onboard. | 22000 | 30 net-new PM owners · 20 investor leads
12 | May 2027 | Phase 1 — Tooele Foundation | Lifecycle storytelling pivot | Launch the "Lifecycle Stories" campaign — short doc-style films of real PUR customers across stages. | First 3 Lifecycle Stories videos go live with companion long-form posts. | $14K paid spend. Heavy video on YouTube + Meta. Geofence Tooele + Stansbury + Grantsville. | Story 1: "From the lake apartment to the lake house" — Stansbury family. | Highland summer event series begins (monthly). | First end-of-Q2 lookback. Phase 1 metrics review. | 22000 | 1,000 video views · 8 inbound video-attributed leads
13 | Jun 2027 | Phase 1 — Tooele Acceleration | Summer relocation push | Wasatch Front relocation campaign — pre-positioning for Phase 2. | "Why Tooele over [Daybreak / Herriman / Magna]" comparison cluster (6 posts). | Scale paid to $16K. Geofence SLC south-side neighborhoods to draw relocation traffic. | Sponsor local SLC podcast (1 month). Test KSL banner placement. | PM mid-year owner survey (NPS). | Begin Phase 2 SLC content research + competitor mapping. | 24000 | 600 leads · 15% of traffic from SLC metro
14 | Jul 2027 | Phase 1 — Tooele Acceleration | Sellers come back to market | "List Confidence" campaign — guarantee instant valuation + listing consult in 24h. | Sellers content sprint: 8 posts. "How to price Tooele" data series. | Google PMAX + seller-keyword push ($16K). | Sponsor Tooele County Fair booth. Mass exposure. | Builder back-half launch: Highland Phase 3. | Internal: hire part-time videographer. | 26000 | 60 listing-side leads · Average days on market ↓ 5
15 | Aug 2027 | Phase 1 — Tooele Acceleration | Back-to-school season + Phase 2 readiness | School-zone landing pages for Tooele district + Grantsville district + private options. | Family-buyer cluster (8 posts). Commute calculator launches. | Family-targeted Meta video. School-keyword Google spend. | Sponsor Tooele HS football season. Premier-branded yardline signage. | PM expansion: Stansbury Park inventory push. | Phase 2 SLC plan finalized + signed off. | 24000 | 700 leads · 25 PM signups
16 | Sep 2027 | Phase 2 — Wasatch Front Entry | Phase 2 launch — Wasatch Front entry | Launch /salt-lake landing hub. Public announcement: "Tooele expertise, Wasatch reach." | First 6 SLC sub-market pages (Daybreak, Herriman, South Jordan, Riverton, Magna, West Jordan). | Geo-expand Google + Meta to SW Salt Lake County ($22K total spend). | PR push: Building SLC, KSL, Salt Lake Tribune, Utah Business Magazine. | Recruit 2 SLC-based agents under Premier brand (independent contractors). | Onboarding for SLC agents. Brand training, voice, lifecycle messaging. | 32000 | 600 SLC sessions/wk · CPL stays <$80 in SLC
17 | Oct 2027 | Phase 2 — Wasatch Front Entry | SLC content engine + retargeting | Launch SLC-specific Lifecycle Stories — Tooele-to-SLC commuter narratives. | 12 SLC-targeted posts + 4 video stories. | $26K spend: Google, Meta, YouTube, LinkedIn (commercial). LinkedIn for PM/investor. | Daybreak community sponsorship. South Jordan Days booth. | Highland Phase 4 launch (could also serve as SLC-commuter alternative). | Monthly review: SLC CPL vs Tooele baseline check. | 30000 | 850 total leads · 40% SLC-sourced
18 | Nov 2027 | Phase 2 — Wasatch Front Entry | Holiday + investor year-end | Year-end investor push: 1031 exchanges, year-end purchases, PM signups for 2028. | Investor cluster: 8 posts on tax, 1031, depreciation, year-end strategy. | $24K spend; LinkedIn investor scale; Google investor keywords. | Tooele Transcript end-of-year feature placement. | PM 2028 ownership-onboarding push. | Hire SLC-based marketing coordinator (part-time). | 28000 | 50 investor leads · 25 net-new PM owners
19 | Dec 2027 | Phase 2 — Wasatch Front Entry | Year-end wrap + 2028 prep | Year-end report: "Premier's Year of the Lifecycle" — public-facing year-in-review. | 2027 Tooele market wrap-up. 2028 Tooele outlook. Both as standalone microsites. | $18K spend (seasonal cooldown). Heavy retargeting only. | Local press end-of-year quotes. Holiday client gifts mailed. | Highland end-of-year sales push with builder incentive. | Team strategy offsite. 2028 plan locked. | 22000 | Site sessions YoY +180% vs Dec 2026
20 | Jan 2028 | Phase 2 — Wasatch Front Entry | 2028 launch | Full launch of SLC dedicated brand campaign (still under PUR umbrella). | 12 SLC neighborhood pages + 8 SLC lifestyle clusters. | $30K spend: aggressive January Google + Meta + YouTube. | January "Tooele 2028 Market Outlook" webinar (Tooele) + SLC version. | SLC Highland-alternative push: "You can build new for $429K in Grantsville." | First quarterly board update on Phase 2 metrics. | 34000 | 1,100 leads · CPL <$60 blended
21 | Feb 2028 | Phase 2 — Wasatch Front Entry | Phase 2 gate check (Month 21) | Phase 2 gate evaluation: SLC CPL, transaction rate, agent productivity. | Continue SLC content cadence (10 posts). | $30K paid. Begin reducing brand-defense if Tooele is healthy. | Phase 2 case study: "Six months in, what worked." | Builder pipeline review with UpDwell. | Go/no-go decision: scale SLC or pause and reinvest in Tooele. | 30000 | GATE: SLC CPL ≤ 1.5x Tooele baseline
22 | Mar 2028 | Phase 2 — Wasatch Front Scale | Scale or consolidate (based on gate) | If GO: scale SLC budget +30%; if NO-GO: reinvest in Tooele depth. | Spring 2028 buyer guide refresh. Tooele + SLC editions. | $36K (GO) or $28K (consolidate). | Annual brand campaign refresh creative concepts. | Highland Phase 5 launch. | Begin discussions for Phase 3 (Year 3 plan). | 34000 | Spring transaction pipeline ≥ 80 deals attributable to digital
23 | Apr 2028 | Phase 2 — Wasatch Front Scale | Spring market peak | Annual Open House festival (12 listings, one weekend). | Spring cluster: 12 new posts; updated 2028 neighborhood data. | $36K — peak spring spend. | Sponsor a marquee Tooele community event (e.g., Bit & Spur Rodeo). | PM portfolio growth push: "Hand us the keys." | Mid-Q2 KPI review. | 36000 | 1,300 leads · 25+ closings · 50 PM signups
24 | May 2028 | Phase 2 — Wasatch Front Scale | 24-month wrap + Year 3 plan | 24-month executive review. Public-facing 2-year impact report. | Pillar refresh: rewrite the 6 strongest pages with 2 years of data. | $32K. Capture full spring tail. | Anniversary press: "Two years since Premier rebuilt the Tooele real estate playbook." | Year-2 builder + PM growth metrics published. | Year 3 strategic plan signed off. | 34000 | Brand search up 4x · 24-mo total leads ≥ 18,000
24-MONTH TOTAL

## Phase Summary
Phase Summary
Phase | Months | Date Range | Theme | Budget | Primary Goal
Phase 0 — Build | 1–6 | Jun 2026 – Nov 2026 | Strategy, design, build, photography, content seeding |  | Ship a launchable site + content + brand foundation
Phase 1 — Tooele Foundation | 7–12 | Dec 2026 – May 2027 | Soft and full launch; Tooele SEO + paid ramp; first transactions |  | Establish Tooele as the dominant brand; CPL <$60
Phase 1 — Tooele Acceleration | 13–15 | Jun 2027 – Aug 2027 | Scale spend; lifecycle storytelling; pre-position SLC |  | Capture spring/summer market; ready Phase 2 launch
Phase 2 — Wasatch Front Entry | 16–21 | Sep 2027 – Feb 2028 | Geographic expansion to SW Salt Lake County |  | Validate SLC market with controlled spend; gate review at M21
Phase 2 — Wasatch Front Scale | 22–24 | Mar 2028 – May 2028 | Scale or consolidate based on gate; spring 2028 peak |  | Year 3 strategic plan; brand search 4x baseline
24-MONTH TOTAL

## Channel Mix
Channel Allocation (Approximate 24-Month Distribution)
Channel | % of Total Spend | Estimated $ | Primary Use | KPIs
Google Ads (Search + PMAX) | 22% |  | Brand defense, high-intent buyer/seller keywords, location-targeted Tooele queries | CPL, CTR, ROAS, ranking impressions
Meta (FB + IG) | 18% |  | Listing video, retargeting, lookalikes, Lifecycle Stories distribution | Lead form fills, CPL, video completion rate
YouTube / Connected TV | 10% |  | Brand video, neighborhood reels, agent intros, pre-roll on local content | Views, watch-through %, brand search lift
LinkedIn | 5% |  | Investor + commercial + PM owner targeting | Form fills, CPL, decision-maker matches
Nextdoor + Local placements | 4% |  | Hyperlocal Tooele awareness, neighborhood-specific posts | Engaged sessions, lead form fills
Content production (writers, video, photo) | 18% |  | Blog posts, market reports, video, photography retainer | Pieces/month, organic rank, time on page
CRM + Marketing automation | 6% |  | Follow Up Boss, Klaviyo, transactional email, dashboards | Email open/CTR, lead lifecycle velocity
PR + Events + Sponsorships | 8% |  | Local press, sponsorships, community events, Highland builder events | Media mentions, event leads, brand search lift
SEO tools + analytics | 4% |  | Ahrefs/Semrush, Search Console, GA4, PostHog, Plausible | Ranking trends, page experience scores
Contingency / experimentation | 5% |  | New-channel pilots, creative tests, audience experiments | Test cycle velocity
TOTAL

## KPI Targets
Key Performance Indicators — Quarterly Targets
Bold = primary success metric for the quarter. All targets assume Path B baseline.
KPI | Q4 2026 | Q1 2027 | Q2 2027 | Q3 2027 | Q4 2027 | Q1 2028 | Q2 2028 | Notes
Monthly Web Sessions | 8000 | 18000 | 32000 | 45000 | 55000 | 75000 | 95000 | Organic + paid + direct
Total Leads / Month | 250 | 400 | 600 | 700 | 800 | 1100 | 1300 | All forms + calls + chat
Blended CPL | 65 | 55 | 50 | 50 | 55 | 60 | 55 | Lower = better; SLC entry will lift temporarily
Cost / Closing | 1800 | 1500 | 1300 | 1300 | 1400 | 1500 | 1300 | Transaction-attributed marketing cost
Net New Lifecycle Accounts | 80 | 220 | 350 | 400 | 500 | 650 | 800 | Account opens, the proxy for relationship depth
Net New PM Owners | 8 | 18 | 22 | 28 | 25 | 35 | 50 | Direct revenue driver, high LTV
Active Listings | 35 | 60 | 90 | 110 | 100 | 130 | 160 | Tooele + Highland + SLC by Q3 2027
Sold-Side Transactions | 12 | 25 | 45 | 55 | 60 | 80 | 100 | Premier as listing agent
Brand Search Volume (index) | 100 | 140 | 180 | 230 | 280 | 350 | 420 | Indexed: Q4 2026 = 100
Organic Keywords Ranking (top 10) | 30 | 95 | 180 | 240 | 310 | 400 | 500 | Tooele + lifestyle + SLC clusters
Email Subscribers | 1200 | 2800 | 5000 | 7500 | 10500 | 14000 | 18000 | Cumulative; market report subscribers + newsletter
Video Views (YouTube + Meta) | 5000 | 30000 | 80000 | 150000 | 240000 | 380000 | 550000 | Cumulative

## Phase 2 Gate
Phase 2 Gate — Month 21 (Feb 2028) Go/No-Go Criteria
If three or more of the five criteria are GREEN, scale Phase 2. If two or more are RED, consolidate and reinvest in Tooele.
Criterion | GREEN (Scale) | AMBER (Hold) | RED (Consolidate)
SLC blended CPL vs Tooele baseline | ≤ 1.3x | 1.3x – 1.6x | > 1.6x
Transactions attributable to SLC paid | ≥ 12 / quarter | 6 – 12 / quarter | < 6 / quarter
SLC organic monthly sessions | ≥ 8,000 | 4,000 – 8,000 | < 4,000
SLC PM signups | ≥ 8 / quarter | 3 – 8 / quarter | < 3 / quarter
SLC agent productivity (transactions / agent) | ≥ 80% of Tooele agents | 60% – 80% | < 60%